## Sheet1
Steps Before Failover Day | Task | Description | Completed
Application shutdown steps
Your other planning steps
Storage Planning Steps
0 | Document DR Runbook plan | Organize steps, contacts, order of steps, contacts per step required on execution of failover day
0A | Submit support logs for failover readiness audit (7 days before planned event) (see image for case option to request assessment) | https://docs.supernaeyeglass.com/articles/#!project-planning-guides/failover-release-notes/a/h2_0
0B | Take failover training labs to practice execution | https://www.supernaeyeglass.com/booking
1A | Review DR Design Best Practices Review Failover Release notes Warning: Mandatory Step for all customers DR Assistance requires acceptance before continuing | https://manuals.supernaeyeglass.com/project-planning-guides/HTML/failover-release-notes.html https://manuals.supernaeyeglass.com/project-planning-guides/HTML/eyeglass-and-isilon-failover-best-practices.html
1B | Upgrade to the latest release to address known issues and updated failover logic | https://manuals.supernaeyeglass.com/project-all-product-installation-and-upgrade-guides/HTML/eyeglass-isilon-edition-upgrade-guide.html
1C | Test DR procedures | Setup Runbook robot feature for continuous DR testing Test failover with Superna Eyeglass Test it again, again and again Failback Review results, logs to ensure steps that Superna Eyeglass executes are understood Consulting documentation on failover mode you planned to implement Execute test plan before failover day to validate procedures
1D | Benchmark Failover (access Zone) | Copy data into a test policy or the runbook robot access zone (note Robot can only use 1 policy for testing, to complete multi policy testing a test access zone would need to be created and configured for access zone failover) Execute test failover and use failover log to find the make writable step time delta to the start of the log. This is the point at which failover is completed, and failback steps now begin to execute but clients are able to write data to target at this point. Repeat above with 2 policies and a known quantity of data so that both policies sync data and failover. Record the make writable time difference log step to the beginning of the failover log time stamp Repeat one more time with 3 policies same amount of data in each directory Now average the 3 test run times to the make writeable step and use this value that is unique to your environment (clusters, WAN, nodes in replication, etc..) to use to calculate estimated failover times if you have more than 3 policies. Note the test access zone should have all configuration completed (hints, spn, shares and exports and quotas) to ensure that the time estimates are as close to production configuration when estimating failover times. Note: If change rate is expected to be zero before planned failover then skip step to create changed data before failover. Note: The reason to create as many shares under each policy as in production is to get the time for the rename step to complete for each share, this step is parallel operation but should be benchmarked on your clusters Note: failover logs include steps post failover to prepare for failback and complete audit of the clusters. The failover job time DOES NOT REPRESENT THE TIME IT TAKES TO FAILOVER. YOU MUST CALCULATE THE MAKE WRITABLE STEP IN THE LOGS
1E | Benchmark Failover (DFS Mode) | Use the Access Zone with DFS mode policy or create a test DFS mode policy Copy test data into path Create one more shares into the path of test policy (if you have more than one share under a policy in production than create as many shares as you have in production policy configuration) Create more than one policy as per above step example 3 to get a good time average Create changed data if you plan to failover with un-synced data (optional step) Run DFS mode failover on 1 policy, then 2 then 3. Record the make writeable step time difference to the start of the failover log. Calculate the average time per policy (based on your production configuration) Use this number to estimate the time to complete your production failover times Note: The reason to create as many shares under each policy as in production is to get the time for the rename step to complete for each share, this step is parallel operation but should be benchmarked on your clusters Note: failover logs include steps post failover to prepare for failback and complete audit of the clusters. The failover job time DOES NOT REPRESENT THE TIME IT TAKES TO FAILOVER. YOU MUST CALCULATE THE MAKE WRITABLE STEP IN THE LOGS
2 | Contact list for failover day | AD administrator DNS administrator Cluster storage Administrator workstation, server administrators Application team for dependant applications Change Management case entered for outage window
3 | Reduce failover and failbacktime - Run manual domain mark jobs on all syncIQ policy paths (this will speed up failover because domain mark can take a long time to complete and elongates the failover time) | https://manuals.supernaeyeglass.com/project-planning-guides/HTML/eyeglass-and-isilon-failover-best-practices.html#h.aifo24syxgut
4 | Count shares,exports, NFS alias, quotas on source and target with OneFS UI | Validates approximate config count is synced correctly (also verify Superna Eyeglass DR Dashboard) (there should be no quotas synced on target - only shares, exports and NFS alias)
5 | Verify dual delegation in DNS before failover | This verifies that DNS is pre-configured for failover for all Smartconnect Zones that will be failed over (Access Zone failover fails over all Smartconnect Zones on all IP pools in the Access Zone)
6 | DFS failover preparation | using dfsutil verify clients that will be failing over show two active paths to storage and that correct path is active Verify all DFS mounts have both referrals configureddfsutil tool downloaded by OS type check path resolution
7 | Communicate to application teams and business units that use the cluster the failover outage impact | Scheduled maintenance window with application and business units Ensure to explain that data loss will occur if data is written passed the maintenance window start time
8 | Set all policies schedule to every 15 minutes or less 1 day prior to the failover to ensure data is staying in sync. This also ensures the failover speed will be optimized | This step is critical step to changne to avoid long running policies or long running jobs that will extend your failover and maintenance window. Specifically ensure run on change is never left enabled since policies that are running cannot be controled for failover.
Steps on the failover Day | Task | Description | Completed
0 | SMB and NFS protocol disable | Determine if this will be used to enforce no writes to source cluster (consult EMC documentation on isi command)
0A | Review running policies and policy run time on all policy in the failover 2 hours before the planned failover. | This step verifies that policies are runninng normally before the planned failover. Take action or open Dell SR if policies are failing or running for unexpected long duration.
1 | Force run syncIQ policies 1 hour before planned failover | Run each syncIQ policy before so that the failover policy run will less data to sync
2 | Execute failover | https://manuals.supernaeyeglass.com/project-design-guides/HTML/how-to-execute-a-failover-with-dr-assistant.html
3 | Monitor failover | https://manuals.supernaeyeglass.com/project-design-guides/HTML/how-to-monitor-the-eyeglass-assisted-failover.html
4 | If Required Data recovery guide | https://manuals.supernaeyeglass.com/project-eyeglass-operations-guides/HTML/failover-recovery-procedures.html
5 | Ensure Active Directory admin is available | ADSIedit recovery steps are required and needs Active Directory Administrator access to cluster machine accounts
After Failover | Test Data Access | https://manuals.supernaeyeglass.com/project-design-guides/HTML/how-to-validate-and-troubleshoot-a-successful-failover-when-data.html